## Process-Based Estimation
Document Name | Number of sections | Estimated Hrs/Section | Total Hours
RMMM | 4 | 2.2 | 8.8 | Note*:Project Documentation estimates are based on the Table of Documentation Working Time
Project Plan | 7 | 2.2 | 15.4 | Note**: Risk Analysis is based on section 2.1.2 for estimations, found by considering Probability and Impact values
Use Case Document | 9 | 3 | 27 | Note***: 1 person-month (pm) = 160 hours
Project Timeline Documents | N/A | 3 | 3 |  | Process-Based Estimation (Person-Months)
Use Case Presentation | N/A | 3 | 3 | Activity--> | Planning | Risk Analysis** | Engineering |  | Construction Release |  | Totals (pm***)
RMMM and Project Plan Presentation | N/A | 3 | 3 | Task --> |  |  | Analysis | Design | Code | Test
Total Hours for All Documents |  |  | 60.2
|  |  |  | Function (below) |  |  | n/a | n/a | n/a
|  |  |  | Project Documentation* | 0.05 | 0.05 | n/a | n/a | n/a | 0.01 | 0.11
|  |  |  | Build Clover 4.2 Drone | 0.45 | 0.4 | n/a | n/a | n/a | 0.01 | 0.86
|  |  |  | Build Pi-Car-X | 0.35 | 0.3 | n/a | n/a | n/a | 0.2 | 0.85
|  |  |  | Manual drone flight | 0.05 | 0.15 | n/a | n/a | n/a | 0.05 | 0.25
|  |  |  | Manual car driving | 0.05 | 0.15 | n/a | n/a | n/a | 0.05 | 0.25
|  |  |  | Autonomous drone flight | 0.1 | 0.05 | 0.2 | 0.15 | 0.35 | 0.1 | 0.95
|  |  |  | Autonomous car driving | 0.1 | 0.05 | 0.2 | 0.15 | 0.25 | 0.1 | 0.85
|  |  |  | Learn and develop sensory data collection interfaces for car and drone | 0.05 | 0.05 | 0.1 | 0.2 | 0.25 | 0.5 | 1.15
|  |  |  | Process vision data (OpenCV) | 0.05 | 0.05 | 0.15 | 0.2 | 0.25 | 0.5 | 1.2
|  |  |  | Build drone-car communication protocol | 0.1 | 0.15 | 0.2 | 0.5 | 0.5 | 0.5 | 1.95
|  |  |  | Totals(pm***) | 1.35 | 1.4 | 0.85 | 1.2 | 1.6 | 2.02 | 8.42
|  |  |  | %Effort (total pm for a category/total pm)* 100(%) | 16.0333 | 16.6271 | 10.095 | 14.2518 | 19.0024 | 23.9905

## Use Case Estimation
Use Case Points Estimation (person-months)
Note: Total weight = person-month estimation; 1 person-month = 160hrs
Use Case | Type | Complexity | Weight | Total Weight (complexity *weight)
Changing Parameters | Change parameters on the drone or car through human API | 2 | 0.1 | 0.2
Running an Experiment | Human API for conducting and running drone-car experiment | 3 | 0.2 | 0.6
Collecting Data | Human and machine (drone or car) interface for collecting and analyzing data | 5 | 0.4 | 2
Actors
Drone | Machine | 5 | 0.5 | 2.5
Car | Machine | 3 | 0.4 | 1.2
Human Facilitator | Human | 1 | 0.1 | 0.1
Human Experimentor | Human | 1 | 0.1 | 0.1
Total (pm) |  |  |  | 6.7
ECF (Environment Complexity Factor) | 1.01
TCF (Techincal Complexity Factor) | 1.02
Total (pm) * ECF * TCF |  |  |  | 6.9023